## Project Timeline
Washington Forms Online
Technology Assisted Forms Project
PHASE |  | DETAILS | Project Q1 (2018) | [12 empty] | Project Q2 (2018) | [13 empty] | Project Q3 (2019) | [11 empty] | Q4 (2019) | [12 empty] | Project Q5 (2019) | [13 empty] | Project Q6 (2019) | [12 empty] | Project Q7 (2020) | [12 empty] | Project Q8 (2020) | [12 empty] | Project Q9 (2020) | [13 empty] | Post-Project (2020-2021)
|  | MONTH: | JUL |  |  |  |  | AUG |  |  |  | SEP |  |  |  | OCT |  |  |  |  | NOV |  |  |  | DEC |  |  |  |  | JAN |  |  |  | FEB |  |  |  | MAR |  |  |  | APR |  |  |  |  | MAY |  |  |  | JUN |  |  |  | JUL |  |  |  |  | AUG |  |  |  | SEP |  |  |  |  | OCT |  |  |  | NOV |  |  |  | DEC |  |  |  |  | JAN |  |  |  | FEB |  |  |  | MAR |  |  |  |  | APR |  |  |  | MAY |  |  |  | JUN |  |  |  |  | JUL |  |  |  | AUG |  |  |  |  | SEPT |  |  |  |  | OCT-DEC |  |  | JAN-MAR
|  | Enter the date of the first Monday of each month --> | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 |  | Oct | Nov | Dec | Jan | Feb | Mar
1 | Planning | - Define project scope, document tentative design decisions | JUL 2: Scope/Design | PROJECT COMPLETION
|  | - select/set up project management tool | JUL 9: PM tool
|  | - Checklist of non-automation element | JUL 30: Checklist
|  | - Determine LHI reporting and data needs | JUL 23: Determine data needs
|  | - Create evaluation plan (requires approval by LSC) | SEP 3: Evaluation plan
|  | - Experience lifecycle of simple prototype | AUG 6: Prototype
|  | - Create Testing Plan | AUG 6: Testing plan
|  | - Action Plan for stakeholder buy-in | AUG 20: Stakeholder plan
|  | - Informed estimate of overall cost of content automation | JUL 2: Estimate overall cost of automation
|  | - Develop overall project plan/timeline | JUL 30: Develop overall plan/timeline
|  | - Identify tentative interviews/bundles | AUG 20: Tentative bundles
|  | - Frame and settle overall scope of contract services | SEP 3: Contract
|  | - Report on planning phase, lessons learned | SEP 17: Report
2 | Ramp up | - Finalize and prioritize interviews/bundles (requires approval by LSC) | SEP 10: Finalize interviews/bundles
|  | - Document interview design decisions | SEP 10: Doc. design decisions
|  | - Develop process maps | OCT 1: Process maps
|  | - Coordination with WaLawHelp re interview presentation pages | OCT 1: Coordination with LawHelp
|  | - Develop templates for supporting content (jump off page FAQ, output instructions, surveys) | OCT 1: Non-automation content templates
|  | - Develop standard closing dialog template for interviews with errata (incomplete) list | OCT 1: Closing dialog template
|  | - Develop content grid to track consistent language across all interviews and staging pages | OCT 1: Content Grid
|  | - Develop testing materials including personas, scenarios, reporting and tracking tools | OCT 1: Testing materials
|  | - Develop business requirements with PBN to implement high priority LHI platform enhancements | OCT 1: Develop business requirements with PBN for LHI platform enhancements
|  | - Meeting with Advisory Committee to review items from planning phase | OCT 15: AC mtg
3 | Automation & Testing | - Develop form templates | OCT 1: Group 1 - templates; FEB 25: Group 2 and 3 - templates; SEP 30: Group 3-4 Templ; OCT 28: Group 4, 5 and 6 - Templates; JAN 13: Group 5-6 - Templates; FEB 17: Group 6-7 - Templates; MAR 23: Group 7-8 - Templates; APR 27: Group 8-9 - Templ; MAY 25: Group 9-10 - Templ; JUN 22: Group 10-11 - Templates; JUL 27: Group 11-12 - Templates; AUG 31: Group 12 - Templates
|  | - Develop interview language and logic | OCT 8: Group 1 - interviews; FEB 25: Group 2 and 3 - Interiews; SEP 30: Group 3-4 Interv; OCT 28: Group 4, 5 and 6 - Interviews; JAN 13: Group 5-6 - Interviews; FEB 17: Group 6-7 - Interviews; MAR 23: Group 7-8 - Interviews; APR 27: Group 8-9 - Interv; MAY 25: Group 9-10 - Interv; JUN 22: Group 10-11 - Interviews; JUL 27: Group 11-12 - Interviews; AUG 31: Group 12 - Interviews
|  | - Develop resource/help text and edit interview text for plain language | NOV 5: Group 1 - resource/PL; MAR 11: Group 2 and 3 - res./PL; NOV 4: Group 4, 5 and 6 - res./PL; JAN 13: Group 5-6 - res./PL; FEB 17: Group 6-7 - res./PL; MAR 23: Group 7-8 - res./PL; APR 27: Group 8-9 - res./PL; MAY 25: Group 9-10 - res./PL; JUN 22: Group 10-11 - res./PL; JUL 27: Group 11-12 - res./PL; AUG 31: Group 12 - res./PL
|  | - Develop supporting content (jump off page, FAQ, output instructions, next steps) | NOV 5: Group 1 - supporting content; MAR 11: Group 2 and 3 - supp. content; NOV 4: Group 4, 5 and 6 - supp. cont.; JAN 13: Group 5-6 - supp. cont.; FEB 17: Group 6-7 - supp. cont.; MAR 23: Group 7-8 - supp. cont.; APR 27: Group 8-9 - supp. cont.; MAY 25: Group 9-10 - supp. cont.; JUN 22: Group 10-11 - supp. cont.; JUL 27: Group 11-12 - supp. cont.; AUG 31: Group 12 - supp. cont.
|  | - Staff testing and revising; react to stakeholder and user testing; track feedback | DEC 3: Group 1 - staff test/revise/react; MAR 18: Group 2 and 3 - staff test/revise; OCT 28: Group 4, 5 and 6 - staff test/revise; JAN 13: Group 5-6 - staff test/revise; FEB 17: Group 6-7 -staff test; MAR 23: Group 7-8 -staff test; APR 27: Group 8-9 -staff test; MAY 25: Group 9-10 -staff test; JUN 22: Group 10-11 -staff test; JUL 27: Group 11-12 -staff test; AUG 31: Group 12 -staff test
|  | - Stakeholder testing | MAR 11: Stakehldr; SEP 9: s/h; JAN 6: s/h; FEB 3: s/h; MAR 2: s/h; APR 6: s/h; MAY 4: s/h; JUN 1: s/h; JUL 6: s/h; AUG 10: s/h; SEPT 14: s/h
|  | - End user testing [tentatively scheduled 3 times] | FEB 25: User; JUN 24: User testing; JUL 29: User testing; JAN 6: User
|  | - Go Live - Publish interviews on LawHelp | APR 1: 1; SEP 30: 2; OCT 28: 3; JAN 20: 4; FEB 17: 5; MAR 16: 6; APR 20: 7; MAY 18: 8; JUN 15: 9; JUL 20: 10; AUG 24: 11; SEPT 28: 12
|  | - Respond to user feedback through LHI and other channels | APR 8: Respond to user feedback through LHI and other channels
4 | Outreach | - Develop outreach plan | FEB 3: Outreach plan
|  | - Coord. with AOC re links from courts website | JAN 7: Coordination with AOC re links from courts website
|  | - Publicize via Monthly LawHelp updates | JAN 6: Upd.; FEB 3: Upd.; MAR 2: Upd.; APR 6: Upd.; MAY 4: Upd.; JUN 1: Upd.; JUL 6: Upd.; AUG 3: Upd.; SEPT 7: Upd.
|  | - Clerk's Association Conference: Jun. 26, 2019 | AUG 13: Clerks; OCT 1: WACO; JUN 24: Pres.
- FJLC/FLEC Annual Joint Meeting [DATES?]
- Spring Judicial Traning [DATES?]
- Facilitators training Sept. 30, 2019
|  | - ATJ Conference June 14-16, 2019 | JUN 10: ATJ
|  | - TIG Conference Jan 9-11, 2019 | JAN 7: TIG; JAN 13: ITC
|  | - Develop WashingtonLawHelp filtering tool | APR 6: WashingtonLawHelp filtering tool; JUL 6: WashingtonLawHelp filtering tool
5 | Administration & Evaluation | - Advisory Committee Mtgs | OCT 22: AC mtg; APR 1: AC Mtg; OCT 7: AC mtg; APR 6: AC mtg
|  | - Monthly reports to OCLA and Advisory Committee | OCT 15: Rep; DEC 3: Rep.; JAN 7: Rep.; FEB 4: Rep.; MAR 4: Rep.; APR 1: Rep.; MAY 6: Rep.; JUN 3: Rep.; JUL 1: Rep.; AUG 5: Rep.; SEP 2: Rep.; OCT 7: Rep.; NOV 4: Rep.; DEC 2: Rep.; JAN 6: Rep.; FEB 3: Rep.; MAR 2: Rep.; APR 6: Rep.; MAY 4: Rep.; JUN 1: Rep.; JUL 6: Rep.
|  | - LSC TIG Milestone Reports | JUL 2: M2; JAN 28: M3; JUL 29: M4; JAN 27: M5; JUL 6: M6 |  |  |  | M7 |  |  | M8
|  | - Evaluation plan approved by LSC | NOV 19: LSC approves eval plan
|  | - Bundles approved by LSC | NOV 19: LSC approves bundles
|  | - A2J Tech Fellow prep, work plan | APR 1: A2J Tech Fellow prep, work plan
|  | - Report on A2J Tech Fellow's service | SEP 2: Report on A2J TF
|  | - Collect data per evaluation plan | NOV 5: Before surveys; JUL 6: Collect data |  | Collect data
|  | - Submit final report to LSC | [119 empty] | Final Report
|  | - Submit final budget to LSC | [122 empty] | Final Budget
|  | - Finalize Evaluation Plan | OCT 1: Finalize Evaluation Plan
|  | - Develop optional user demographic survey | OCT 1: Develop demog. survey
- Assess usage data (quarterly & bi-weekly after first launch)
6 | Sustainability | - Develop local programming capacity
|  | - Online HotDocs programming training Aug-Sept 2018 | AUG 27: Online Training
|  | - In-person HotDocs & A2J Author training pre-TIG conf. Jan. 7-8, 2019 | JAN 7: TIG
|  | - Local programmer to assist in testing and revision (beginning in 2019) | JAN 14: Local programmer to assist