## Sheet1
RIGHT TO COUNSEL IMPLEMENTATION STATUS -- PER JUDICIAL DISTRICT -- Updated Through 12/13/21
Judicial District | OCLA-Contracted RTC Providers | Attorneys Hired and Trained by 10/1/21 (y/n) | RTC Provider/Court Protocol Established (y/n) | OCLA Certification to Presiding Judge (date)
Hells Canyon (Asotin, Garfield, Columbia) | Northwest Justice Project -- Pullman. | Attorney hired with a start date of 1/3/22 | Yes, both filed and unfiled
Benton-Franklin | Northwest Justice Project -- Kennewick (EPU) | 2 of 3 hired and trained; additional SE regional gap attorney authorized
Walla Walla County |  | See Benton Franklin County | Yes, both filed and unfiled
Chelan County | Northwest Justice Project -- Wenatchee (EPU); Chelan-Douglas Volunteer Attorney Program | Yes | Yes, both filed and unfiled | 2021-10-04
Douglas County | Northwest Justice Project -- Wenatchee (EPU); Chelan-Douglas Volunteer Attorney Program | Yes | Yes, both filed and unfiled | 2021-10-04
Grant County | Northwest Justice Project -- Wenatchee/Quincy (EPU); Chelan-Douglas Volunteer Attorney Program | Yes | Yes, both filed and unfiled | 2021-10-13
Clallam County | Northwest Justice Project -- Port Angeles (EPU) | Yes | Yes, both filed and unfiled | 2021-10-20
Jefferson County | Northwest Justice Project -- Port Angeles (EPU) | Yes | Yes, both filed and unfiled | 2021-10-20
Skamania County | Clark County Volunteer Lawyers Program; Northwest Justice Project -- Vancouver (EPU) | Yes | Yes, both filed and unfiled | 2021-10-01
Clark County | Clark County Volunteer Lawyers Program; Northwest Justice Project -- Vancouver (EPU) | Yes | Yes, both filed and unfiled | 2021-10-01
Stevens/Pend Oreille Counties | Northwest Justice Project -- Contract Attorney Program | yes | Yes, both filed and unfiled | 2021-10-07
Cowlitz County | Northwest Justice Project -- Longview (EPU) | Yes | Yes, both filed and unfiled | 2021-10-01
Whakiakum County | Northwest Justice Project -- Longview (EPU) | Yes | Yes, both filed and unfiled | 2021-10-01
Spokane County | Northwest Justice Project -- Spokane (EPU); Spokane County Bar Assn. Housing Justice Project | yes | Yes, both filed and unfiled | 2021-10-18
Lincoln County | Northwest Justice Project -- Spokane (EPU) | yes | Yes, both filed and unfiled | 2021-12-13
Mason County | Thurston County Volunteer Lawyers Program; Northwest Justice Project -- Olympia (EPU) | Yes | Yes, both filed and unfiled | 2021-10-08
Pacific County | Thurston County Volunteer Lawyers Program; Northwest Justice Project -- Olympia (EPU) | Yes | Yes, both filed and unfiled | 2021-10-01
Lewis County | Northwest Justice Project -- Olympia (EPU); Thurston County Volunteer Lawyers Program | Yes | Yes, both filed and unfiled | 2021-10-01
Grays Harbor County | Thurston County Volunteer Lawyers Program; Northwest Justice Project -- Olympia (EPU) | Yes | Yes, both filed and unfiled | 2021-10-01
Thurston County | Thurston County Volunteer Lawyers Program; Northwest Justice Project -- Olympia (EPU) | Yes | Yes, both filed and unfiled | 2021-10-01
Whatcom County | Northwest Justice Project -- Bellingham (EPU); LAW Advocates conflict counsel | yes | yes, both filed and unfiled | 2021-11-15
Island County | Northwest Justice Project -- Bellingham (EPU); LAW Advocates conflict counsel | See Whatcom County | Yes, both filed and unfiled | 2021-11-15
Skagit County | Skagit Legal Aid | Yes | Yes, both filed and unfiled | 2021-10-01
San Juan County | Skagit Legal Aid | See Skagit County | Yes, both filed and unfiled | 2021-10-01
King County | King County Bar Association Housing Justice Project | Yes | Yes, both filed and unfiled | 2021-10-01
Kitsap County | Kitsap Legal Services | Yes | Yes, both filed and unfiled | 2021-11-15
Klickitat County | Northwest Justice Project -- (EPU) | Yes | Yes, both filed and unfiled | 2021-10-01
Kittitas County | Northwest Justice Project -- Yakima (EPU); Yakima Volunteer Attorney Program | waiting for attorney availability | Yes, both filed and unfiled | 2021-11-15
Yakima County | Northwest Justice Project -- Yakima (EPU); Yakima Volunteer Attorney Program | waiting for attorney availability | Yes, both filed and unfiled | 2021-11-15
Pierce County | Tacomaprobono Housing Justice Project | Yes | Yes, both filed and unfiled | 2021-10-01
Snohomish County | Northwest Justice Project -- Everett- (EPU); Snohomish County Legal Services | Yes | Yes, both filed and unfiled | 2021-10-01
Okanogan County | Northwest Justice Project -- Contract Attorney Program | N/A | Yes, both filed and unfiled | 2021-10-01
Adams County | Northwest Justice Project -- Contract Attorney Program | N/A | yes, both filed and unfiled | 2021-10-13
Whitman County | Northwest Justice Project --Pullman | N/A | Yes, both filed and unfiled